**IT INVESTMENT CAPITAL FUND**

**PROJECT STATUS REPORT**

**To:** Information Technology Strategy and Investment Committee

John Vittner, Office of Policy & Management

**FROM:** Shirley Adams

**AGENCY/PROJECT NAME:** Board of Regents – CT Education Academy

**PROJECT MANAGER:** Shirley Adams

**REPORTING PERIOD:** Project Inception through 12/31/2019

**Total Funds Requested:** $ 1,857,615

**Bond Commission Approval(s):** Date: Jan. 2014 Amount: $ 1,595,838

Date: Feb. 2018 Amount: $ 261,777

**Accumulative Total Capital Fund Expenditures to Date:** $ 1,723,100 (as of 12/31/2019)

**Brief Project Description/Summary:**

The CT Education Academy is an eLearning and recording keeping ecosystem designed and built for the State of Connecticut workforce; it provides a central online location/platform for employees, and related constituents, to access many State mandated training courses as well as professional development opportunities.

**Summary of Progress Achieved to Date:**

**January-June 2014**

During the first six months, the initial set of specifications was drafted for the program and the development of the administrative and learning system platforms, as well as the Department of Administrative Service’s *Active Shooter Response* course, had begun.

**July-December 2014**

During the next six months, the first phase of the CT Education Academy administrative system was finalized to accommodate web-based training. (A summary of functionality is included as Attachment A.) A high-availability designed Blackboard learning system was also fully deployed during this time. Additionally, the *Active Shooter Response* course development was completed.

In November 2014, a group of 30 state employees connected to state training and education efforts were invited to pilot the finalized *Active Shooter Response* course within the CT Education Academy system. The feedback provided by the pilot users was collected and addressed in system and course improvements throughout the month of December in preparation for the next, larger pilot group scheduled for early 2015.

**January – June 2015**

In February 2015, a second pilot group containing 120+ Department of Administrative Services employees and 80+ Charter Oak State College employees completed the *Active Shooter Response* course within the CT Education Academy platform. The pilot feedback coupled with the course evaluations provided additional information to further enhance the program and was implemented during this time period. A full quality assurance process was completed on the system and course in preparation for a state-wide launch.

Also from February through April, we visited state agencies currently utilizing SABA for online learning to ascertain what system features would be required in the CT Education Academy platform to accommodate current business processes in the SABA system. During the visits, we were able to determine current business practices and processes needing to be addressed as well as current processes in need of improvement and missing functionality in the current system. We gathered this information to develop a Phase 2 road map for the CT Education Academy program. The Phase 2 plan will not only provide similar functionality, but will provide enhanced processes and additional features. We are waiting for confirmation that Phase 2 will be approved and funded.

In March 2015, the Advisory Council had its inaugural meeting. This group was orientated to the CT Education Academy program and asked for feedback on how to best serve the state. The Advisory Council will be asked to help guide the future direction of the program and help determine the state’s current training needs.

In May 2015, the initial stage of course development was started on the *Workplace Violence Preventio*n course.

In June 2015, the Executive Steering Committee met to discuss a roll-out strategy to the state agencies interested in the *Active Shooter Response* course and the CT Education Academy platform.

**July-December 2015**

In late July, the Commissioner’s office sent a state-wide message about the availability of the *Active Shooter Response* course and the steps for onboarding for the CT Education Academy. From that point, CTDLC coordinated and facilitated over **20 visits** to interested agencies. During the visits, CTDLC performed a readiness assessment with agency representatives to ensure minimum technical requirements were met and performed training for the designated agency administrators within the CT Education Academy platform.

Also, a new release of the CT Education Academy platform was launched in August. This version offered an improved user experience, enhanced reporting, and additional program and onboarding information for interested agencies.

In addition, the *Workplace Violence Preventio*n course development neared completion. The course is ready for piloting. Once the pilot feedback has been processed, the final alterations and media elements will be completed.

Lastly, the Executive Steering Committee continued to discuss potential SABA LMS migration to the CT Education Academy platform. After reviewing the Academy product road map and the SABA agencies’ function requests, a conversation regarding further needs analysis was had.

**January-June 2016**

The CT Education Academy continues to expand the number of agencies accessing the system, the number of courses being offered, and the functionality of the core platform. CTDLC has coordinated and facilitated **33 visits** to interested agencies to date, assessing technical readiness while performing training for the designated agency administrators within the CT Education Academy platform.

Many of the agencies have joined the Academy to access the *Active Shooter Response* course, now totaling over **3,000 enrollments** since its launch in August 2015.

A select number of state employees were invited to pilot the *Workplace Violence Prevention* course this past February. Based on the feedback of those users, improvements were made and the final version of *Workplace Violence Prevention* was launched state-wide in June.

Also launched in June, the **Office of State Ethics** released their *Ethics 101* course to the CT Education Academy audience. The course was modified to include a comprehension-based final, a standard established at the start of the CT Education Academy program. As a result, only a passing grade will grant a learner a certificate of completion, as it demonstrates a basic understanding of the curriculum has been met.

During the February to June timeframe, **Criminal Justice Information System** piloted the CT Education Academy platform to support their state-wide law enforcement training curriculum which serves state, municipal and private law enforcement agencies. Feedback gathered from this pilot group is being addressed in the next two releases on the platform.

The platform was upgraded to version 1.1 in February. This release focused on improvements in reporting, organization management, course management, and overall platform security.

Lastly, the team has been assessing and revising the *Sexual Harassment Prevention* curriculum obtained through the State of Washington to suit the needs of the State of Connecticut.

**July-December 2016**

The CT Education Academy continues to grow in usage and interest. Since August 2015, the Academy has had over **6,800** enrollments (more than double since the last report) across more than **40 State agencies** and 6 towns.

While additional agencies continue to express interest in the Academy for state trainings, an even greater number of agencies are exploring the Academy as a vehicle for their own training delivery. Currently, the **Department of Administrative Services**, **Office of State Ethics**, and **Criminal Justice Information System** are utilizing the Academy platform to manage their online training offerings while the **Department of Motor Vehicles**, **Office of Education and Data Management**, and **Department of Rehabilitation Services** have been piloting the system for select courses.

In 2017, the following agencies will be utilizing the CT Education Academy to manage their online and/or in-person training offerings: the **Office of Education and Data Management** and **Department of Rehabilitation Services** will transition from pilot programs to full production while the **Department of Banking** and **Department of Energy & Environmental Protection** will begin new programs.

During the July to December timeframe, version 1.2 of the Academy platform was launched (August 2016), which contained new reporting functions as well as improvements to the course creation and permission granting processes. During this timeframe, version 1.3 was also developed, which is scheduled to launch on February 1, 2017. The version 1.3 release will focus on the management of in-person trainings and offer additional system roles, roster management tools, and reporting options.

In September 2016, the DAS project liaison left State service, which impacted the course development schedule. The *Sexual Harassment Prevention* training, which was nearly complete, needed final approval of course content. With his departure, and no one to facilitate this final course review step, the progression of the Sexual Harassment Prevention training course stalled. Additionally, we had begun several planning sessions and course content review for a new *LEAN 101* course, which also went dormant since his departure. In December, however, DAS did assign a new content expert to the Sexual Harassment Prevention course to facilitate the final content review in preparation for the course to pilot. Based on this development, we hope to launch this course in early 2017.

Lastly, in December, the **Board of Regents of Higher Education** agreed to list the *State In-Service Training Catalog* within the CT Education Academy platform. All **130 courses** are currently listed and available for registration. This achievement will save agencies countless hours of manual entry of the catalog into their individual training systems as well as the transcription of the completed courses.

**January-June 2017**

Continuing its steady growth, the CT Education Academy has supported over **6,000 unique users** from **89 different agencies/organizations**, accessing **67 different courses** with over **9,000 enrollments** since the program’s inception.

Some growth can be contributed to the inclusion of the *State’s In-Service Catalog* within the platform. All 130 course/sections offered by the CT Community Colleges were available for registration within the Academy for the spring 2017 semester. This listing was implemented in order to save agencies countless hours of manual entry of the catalog into their individual training systems as well as the transcription of the completed courses.

Other usage growth can be attributed to an increase in the number of agencies hosting their own training courses on the CT Education Academy. In addition to the **Office of Education and Data Management,** the **Department of Banking** and the **Department of Consumer Protection** have signed on to utilize the Academy platform for their training management. Both the **Department of Motor Vehicles** and **Department of Rehabilitation** **Services** ran successful pilots on the platform. The **Department of Energy and Environmental Protection** is making final preparations to deliver their first of three training on the Academy platform this fall. The **Connecticut State College & University** system is currently evaluating the Academy platform to assume all of its employee training needs for the upcoming year.

During the January to June timeframe, *version 1.3* of the Academy platform was launched (February 2017), which offered new capacity for agencies to manage their in-person (face-to-face) training needs. The platform now enables the scheduling, enrollment, and roster management of in-person trainings, including dynamic sign-in sheets, roster communication, and reconciliation. Additionally, new reports were designed for agencies delivering training on the Academy platform.

Lastly, after a long hiatus, some additional work was performed on the *Sexual Harassment Prevention* course only to stall again just short of completion and launch. Unfortunately, final approval has not been granted for this course’s release to the state workforce. At this time, it unclear if DAS will move forward to finalize and release the *Sexual Harassment Prevention* course as a state workforce offering. Additionally, all discussions about the development of a *LEAN 101* course and *New Manager’s Orientation* course have ceased at the request of the DAS’ subject matter experts.

To better serve the CT Education Academy agency administrator users, the development of a training course focused on CT Education Academy features, tools, and best practices has begun.

**July-December 2017**

The CT Education Academy usage continues to grow. It now supports **more than 7,000 unique users** from **more than 120 different agencies/organization units** with **more than 11,000 enrollments** since inception.

Some growth can be attributed to expanded usage at agencies like the **Department of Motor Vehicles** and the **Department of Energy and Environmental Protection** for their own training programs. The **Office of Early Childhood** in conjunction with **Eastern Connecticut State University** also launched a pilot course during this period which represents the first course in a series of 9 courses scheduled to launch during 2018.

Agencies such as the **Connecticut State College & University** (CSCU) system and **Connecticut Health & Education Facilities Authority** continue to evaluate and/or pilot the CT Education Academy for broader usage. CSCU is looking to transition all training to the Academy within the next fiscal year.

Also, during this period, **DAS** and the **Connecticut Training & Development Network** (CTDN) hosted a gathering of state-wide training professionals to discuss state-wide training needs. The CT Education Academy was mentioned as a possible solution for a centralized, collaborative training hub. The CTDN leadership will be focusing a future half day workshop on the CT Education Academy program.

In addition to the DAS/CTDN event, CTDLC staff have been invited to partner with DAS HR to evaluate the feasibility of deploying commercial courseware within the Academy platform in order to address mandatory training requirements such as **Sexual Harassment Prevention**.

Lastly, the planning of ***version 1.4*** of the Academy platform began during this period. This new release, which launched in March 2018, will provide agencies with the ability to extend enrollment invitations to constituents that reside outside the state workforce and the ability to manage policy compliance/attestations.

**January – June 2018**

The CT Education Academy usage continues to grow. It now supports more than 266 different agencies/organization units of which 242 are active with more than 14,500 enrollments and 16,000 users since inception.

Agencies like the Department of Motor Vehicles, the Department of Energy and Environmental Protection and the Office of Early Childhood in conjunction with Eastern Connecticut State University continue to growth their usage of the Academy in support of their own training programs.

Also, during this period, the Connecticut Training & Development Network (CTDN) hosted a workshop that focused on the CT Education Academy program and how it may be used as a centralized learning center for state agencies.

In addition to the CTDN event, Charter Oak State College leadership have been asked to address the mandatory training requirement of Sexual Harassment Prevention and revisit the courseware provided by the State of Washington.

Lastly, the development of version 1.4 of the Academy platform began during this period. This new release will provide agencies with the ability to extend enrollment invitations to constituents that reside outside the state workforce and the ability to manage policy compliance/attestations.

**July 2018-December 2018**

In the Spring of 2018, Charter Oak made the decision to dissolve the CTDLC and to continue some of its operations under the college. As part of this decision, a number of CTDLC staff were dismissed at the end of December, including the course developers and some of the IT support staff. The work involved in continuing to support the existing contracts were transitioned over to other staff.

The College completed the revisions to the Sexual Harassment course for DAS and is working with DAS to install it on the CEA platform. The refreshed version of the Hazardous Waste course was launched and Modules 1,2,4, and 7 of the IWWA courses were completed for DEEP, leaving three more to be finished this spring. The 9 modules for Eastern Connecticut State University have been developed and were launched in December, the OER versions have been developed, and Module 1 was developed in Spanish, leaving 8 more modules to be developed in Spanish. Meetings have been held with Department of Vocational Rehabilitation Services to begin planning for upgrades and developments of new courses.

We are continuing to support our Connecticut Education Academy user base. In the final quarter of calendar year 2018, additional sections of the Ethics 101 and Workplace Violence Prevention courses were opened. We worked closely with the CT Dept. of Motor Vehicles, to launch the latest section of their Protecting Sensitive Information training course. We also ensured that additional sections of the Active Shooter course were in place, to allow the DMV’s 800+ agency employees to consume the online training.

The Department of Energy and Environmental Protection launched their Hazardous Waste Management Training in the Academy, in late November. This course had previously been hosted in another learning management system. This is the second course offered by DEEP in the Academy, the first being the Aquifer Protection Area Program Technical Training course. A custom signup form has been implemented, allowing DEEP users to sign up for both courses offered by the agency.

Finally, we have worked with Criminal Justice Information Services, to get their users into the latest iterations of their three training courses offered via the Academy.

**January 2019 – June 2019**

All active CEA courses have been transitioned from the self-hosted Blackboard platform to Blackboard SaaS’s cloud based solution. No major issues were encountered during the migration process.

To date, the SaaS environment has proven to be a reliable system that connects to the custom CEA registration platform seamlessly. End users have expressed satisfaction with the overall performance of the system.

The College is still working with DEEP on the development of their third course. Progress has been slow due to the workload of their content expert.

An overall enrollment report is attached.

**June 2019-December 2019**

New course schedules for the upcoming year were entered in the CEA registration system. Those corresponding course shells were created and populated with content in the Blackboard system, and prepped for use by Learners. New Organizational Administrators were added as necessary, and provided training to administer user account creations for their respective agencies.

Technical Support issues pertaining to the CEA were handled by Charter Oak State College’s support team. These included, but were not limited to, enrollment issues, the transfer of user accounts from one state agency to another, course grading issues, and login issues.

The DEEP course is undergoing final review by DEEP.

During this period, the following courses were opened:

Workplace Violence - 2 sections opened in Dec. 2019, currently 109 learners enrolled.

Active Shooter - 2 sections opened mid-Nov. 2019, currently 15 learners enrolled.

Ethics 101 - 2 sections opened in Nov. 2019, currently 61 learners enrolled.

**Issues and Risks:**

Based upon conversations between Charter Oak State College, the Department of Administrative Services and various participating agencies; there was no solution to migrate course content from the current CEA platform to a platform already in use by DAS or a newly purchased platform owned by individual agencies prior to January 2020. As a result, Charter Oak sought to identify sources of funding to extend the program for a time period sufficient enough to allow all users to migrate content away from CEA. Successful funding sources have been identified comprised of amounts recovered from the LMS vendor for services not utilized between 2014 – 2016, remaining funds available for the project and further reductions to operating costs.

**Next Steps & Project Milestones:**

At the current time, the CEA program will sunset in December 2020 which will be subsequent to the rollout of several HR training initiatives being implemented by DAS. It is anticipated that agencies currently utilizing CEA for statewide mandatory training will be able to leverage the HR initiatives previously mentioned through a project directed by Nicholas Hermes in Fall 2020. Those agencies with custom content will need to work with DAS or other LMS providers on a case by case basis.